## Sheet1
Task | Start date | Due date | Duration
Specifications Document (Zach & Casey) | 2015-12-01 | 2015-12-15 | 14
Proposal (Zach & Casey) | 2015-12-01 | 2015-12-15 | 14
Select specific components to use (Team) | 2015-12-15 | 2016-01-25 | 41
Preliminary Design Review Slides (Zach & Casey) | 2016-01-01 | 2016-01-25 | 24
Procure components (Zach & Casey) | 2016-01-01 | 2016-01-25 | 24
Preliminary Design Review (Team) | 2016-01-27 | 2016-01-28 | 1
Configure serial communications PC / microcontroller (Zach & Justin) | 2016-01-15 | 2016-02-08 | 24
Write software to ingest and process image (Casey) | 2016-01-25 | 2016-02-08 | 14
Test components individually (Team) | 2016-01-15 | 2016-02-10 | 26
Configure communications from microcontroller to motor driver (Zach) | 2016-02-09 | 2016-02-20 | 11
Find method to convert image to G-Codes (Justin & Casey) | 2016-02-09 | 2016-02-20 | 11
Design mechanical system (Tate) | 2016-01-20 | 2016-02-29 | 40
Impliment parser for g-code files (Justin) | 2016-02-20 | 2016-03-15 | 24
Write software GUI and interface (Casey) | 2016-02-21 | 2016-03-15 | 23
CDR Slides (Zach & Casey) | 2016-03-01 | 2016-03-15 | 14
Procure mechanical system components (Tate & Casey) | 2016-03-04 | 2016-03-15 | 11
Design and impliment feedback system (Tate, Zach, Casey) | 2016-03-05 | 2016-03-15 | 10
Critical Design Review (Team) | 2016-03-15 | 2016-03-16 | 1
Mathematically Model System (Tate, Zach, Casey) | 2016-02-20 | 2016-03-25 | 34
Impliment and calibrate laser control system (Zach) | 2016-02-21 | 2016-03-25 | 33
Integrate G-Code interpreter into microcontroller (Justin) | 2016-03-15 | 2016-03-25 | 10
Machine Parts (Tate) | 2016-03-15 | 2016-03-31 | 16
Assemble system (Team) | 2016-04-01 | 2016-04-08 | 7
Testing and Verification (Team) | 2016-04-08 | 2016-04-29 | 21
Write User's Manual (Zach & Casey) | 2016-04-01 | 2016-04-29 | 28
Write Final Report (Zach & Casey) | 2016-04-01 | 2016-04-29 | 28
Design poster (Zach & Casey) | 2016-04-15 | 2016-04-29 | 14